## Sheet1
How do complexity factors and and capability barriers relate to each other? | 1 Strategic importance | 2 Stakeholders/ Influencers | 3 Requirements and benefit articulation | 4 Stability of overall context | 5 Financial impact and value for money | 6 Execution complexity (including technology) | 7 Interfaces/ Relationships | 8 Range of disciplines and skills | 9 Dependencies | 10 Extent of change | 11 Organisational capability: performance to date | 12 Interconnectedness
| the project is critical to delivery of policy, expectations for benefits are high and there is keen external interest (political, public, media); failure would have major negative consequences. | there is a large number of influential stakeholders with diverging objectives or expectations; membership of stakeholder groups may change over time. | the requirements and benefits are ambiguous and their relationship to goals, vision and values is unclear; the impact(s) of the project may be uncertain. | there is a high risk of changes to project scope, structure, and/or external requirements and circumstances with a low level of certainty about planning, costs, governance and/or necessary buy-in. | the costs are subject to change, funding required is organisationally significant and benefits are crucial to organisational goals. | new and/or untested practices, methods and/or technologies are required and objectives are challenging with limited risk management possible due to immovable deadlines or project demands. | the project crosses many boundaries (organisational, political, geographic); success depends on relationships with partners and aspects outside organisational control; governance is complex. | a large number of skills and high level of knowledge are required that are not readily available and/or easily and quickly acquired. | other projects heavily depend on the success of this project. | significant and fundamental organisational change is required to deliver project outcomes and benefits. | there is no history of successfully delivering similar projects; organisational culture is rigid/unresponsive to external changes and unconcerned with adopting good practices. | the relationships between policy, culture, practices, technology, people, processes and procedures are unexplored and lack documentation.
Vision and Value
Reactive or short-term perspective. | High | Low | Moderate | High | Low | Low | Moderate | Low | Moderate | High | High | High
Political priorities compromise good practice. | High | Moderate | Moderate | Low | Low | Low | High | Low | High | Moderate | High | Low
Poor planning (inadequate, uncoordinated or insufficient). | Moderate | Low | Low | Low | Low | Moderate | Moderate | Low | High | Moderate | High | None
Lack of agreed outcomes. | High | Moderate | High | High | Low | Low | Moderate | None | Moderate | Moderate | Moderate | Low
Inability to articulate a clear vision. | High | Moderate | High | Low | Low | Low | Moderate | Low | Moderate | Moderate | Moderate | Moderate
Vision is not part of wider transformation agenda. | Moderate | Low | Moderate | Moderate | Low | Low | High | Low | Low | High | Moderate | Moderate
Poor management of risks or contingencies. | High | Moderate | None | High | Moderate | Moderate | Low | Low | Low | None | Moderate | Low
Overemphasis on creating a bespoke solution. | None | Low | None | Low | Moderate | Moderate | Low | Low | None | Low | Low | None
Leadership and Governance
Insufficient leadership of change. | Low | Low | Low | Moderate | High | High | Low | Low | None | High | Moderate | Low
Tokenistic or limited consultation on objectives. | None | High | Moderate | Low | Low | None | Low | None | Low | Low | Moderate | Low
Funding arrangements do not align with programme/project requirements. | Moderate | Low | Low | High | High | Low | Low | None | Moderate | None | Low | None
Lack of agreed outcomes. | Moderate | None | None | High | Low | Moderate | High | Low | Moderate | Moderate | Low | Low
Insufficient or unclear governance structures. | Low | High | None | High | Low | Low | High | None | Low | High | Low | Low
Lack of resilience and/or adaptability to circumstances | Moderate | High | None | High | Low | Moderate | Moderate | Low | Low | High | Low | None
Insufficient visibility and engagement with communities/stakeholders. | High | High | Low | Moderate | Low | None | High | Low | Low | None | Low | None
Lack of investment in organisation/team capability. | Moderate | None | None | High | Low | High | Low | High | None | Low | Low | Low
Visible difference in assumptions, styles and working languages. | Low | High | Moderate | Low | None | Low | High | Low | Low | Moderate | Low | High
Integrated Working
Programmes/projects managed as discrete entities without regard to links to other programmes/ projects. | Moderate | Low | Low | Low | Moderate | None | High | Low | High | Low | None | Low
Practice or focus limitations compromise the delivery of outcomes. | High | None | Low | None | None | High | Moderate | Moderate | Low | Moderate | High | Low
Culture is suspicious or not transparent. | None | High | Low | Low | Low | Moderate | High | Low | Moderate | Low | High | Low
Poor strategic awareness of partner(s)’ capacity or capability. | Low | High | Low | Low | None | Moderate | High | Low | Low | None | Low | None
Reluctance to learn from experiences or external stakeholders. | Low | High | Low | Low | Low | Moderate | High | Moderate | None | Low | Low | Low
Partnerships do not result in expected benefit(s). | Moderate | High | Moderate | Low | None | None | High | Low | Low | None | Low | None
Highly risk averse regardless of real risk levels. | Low | Low | Low | High | Low | Moderate | Moderate | Low | Low | Low | Low | None
Outcomes and Accountability
Inappropriate transfer of risks. | Moderate | Moderate | Low | Moderate | Low | Moderate | Low | None | Moderate | Low | Moderate | Low
Lack of clear accountability for outcomes (unclear pathways). | High | Low | High | None | Low | None | High | None | Moderate | Low | Moderate | None
Technology viewed as a panacea. | None | None | None | None | None | Moderate | None | High | None | Low | None | Moderate